## 2026 Deliverable (Summary)
Stream No | Stream | Category | Capability Area | Solution Detail | Deliverable Focus Area | Status | Timeline
2 | Unstructured Data for AI | L3 — Preparation & Normalisation | Document Studio Integration | • Integrate Document Studio as the primary ingestion and extraction path for unstructured documents. • Supports modality routing, PDF/Word/HTML parsing, OCR for scanned documents, and initial metadata extraction. • Replaces fragmented use-case-specific parsing with a Group AI managed shared service. | Document Studio | 🟢 Live (Integration required) | Target: Q4 2026 (Initial Integration)
2 | Unstructured Data for AI | L4 / L8 — Semantic Processing & Retrieval | RAG Studio Integration | • Integrate RAG Studio for enterprise embedding generation and retrieval orchestration. • Provides governed model selection, chunking policies, and RAG runtime support. • Establishes the foundation for governed semantic search and AI consumption. | RAG Studio | 🟢 Live / 🟠 Planned (Chunking) | Target: Q4 2026 (Initial Integration)
2 | Unstructured Data for AI | L4 / L5 — Orchestration & AI Integration | MCP Agent Hub Integration | • Integrate the MCP Agent Hub to provide governed tool access from AI runtimes. • Enables stateful agent execution, MCP Client/Gateway mediation, and secure enterprise integration patterns. • Essential for secure copilot and agentic workflows. | MCP Agent Hub | 🟢 Live (Integration required) | Target: Q4 2026 (Initial Integration)
2 | Unstructured Data for AI | L5 / L9 — AI Integration & Controls | Group AI Platform Integrations (LLMs & Moderation) | • Establish managed access to Group AI foundation models, fine-tuned LLMs, and embedding models. • Implement output-side content moderation and guardrails. • Integrate basic AI observability telemetry for model tracking. | LLM & Moderation | 🟢 Live (Integration required) | Target: Q4 2026 (Initial Integration)
2 | Unstructured Data for AI | L6 / L9 — Persistence & Cross-Cutting | Metadata & Lineage Storage | • Implement persistent storage for operational, business, and processing lineage metadata. • Ensure enterprise catalogue alignment for unstructured data products. • Establish end-to-end traceability from source to consumption. | Metadata & Lineage Storage | 🟡 Pattern Exists | Target: Q4 2026 (Initial integration)